## Slide 1
TCH Continuing Education
Project Requested
RFS submitted to CME/CNE
7 Months Out
4 Months Out
CME/CNE communicates receipt within 1 week of request being submitted
Set agenda 4 months out
Obtain all speaker forms required
Due 6 weeks before conference
Due 2 weeks before conference
Input information into CE platform
6 Months Out
Submit all speaker presentations
Should be completed at least 7 months in advance
Conference

## Slide 2
TCH Continuing Education
CME Requesting Coordinator/Committee/Activity Director Responsibilities
Please review checklist for in-depth items to be completed
During CME Activity
Post Activity and Post-Post Activity
Pre-CME Activity
Use sign in option via texting on cell for all events
If educational, attestation for distribution
Announcements of disclosure to audience
Case Conference Checklist
Verification of disclosure at event
Data (outcomes, surveys) and course review
Final budget if indicated
Collect from Speaker requested forms and submit to CE platform (CME/CNE)
  Pre-CME Activity Forms, Addendum A-N as indicated
Collect presentations from speakers

## Slide 3
Quality Education, Simulation, and CME Team
CE Teams Responsibilities
During CME Activity
Post Activity and Post-Post Activity
Pre-CME Activity
Ensure platforms are working and all codes are given to team
Work with team to get items to close out event
Set up meeting with requestor within 3-5 business days
Send email of expectations/guidelines
Identify Operational Leader
  Email should go to them as well with expectations

## Slide 4
  Determine your speakers/presenters
  If seeking CE credits, apply for them
  Advertise (if having CE, this can not be done without CE approval from CME/CNE)
  Utilize TCH CE platform for registration/document collection/etc.
  Determine resources needed
    Costs/Budget
      Venue
      Speakers
      Food
      Marketing
  Evaluate and measure the success
How to Conference Check- List
TCH Continuing Education
  Planning Committee:
  Set dates and conference space
  Create a detailed timeline
  Request for service through CME/CNE
  Application in CE Learning Platform
    Clear goals/objective are set for conference
  Design sessions and tailor to fit the needs of the audience